## Sheet1
| Priorities | Dependencies | Ofplugin | Ofjava | controller(NSF) | ETA | Changed ETA | Comments | Notes
OF 1.3
Configurational State
Flow | 1 |  |  |  | Ed | Done
Meters | 2 |  |  |  | Ed | Done
Groups | 2 |  |  |  | Ed | Done
PortConfig | 3 |  | Ed |  | Ed | Eaw - debugging - 12/20
TableConfig | 3 |  | Hema |  | Hema | Prioritized until after Set Field, may not make it in
Operational State
Switch Features | 1 |  | Juraj |  | Juraj | Done
TableFeatures | 2 |  | Hema |  | Hema | 2013-12-19 |  | Function parked because some switches crash when receiving TableFeatures message
MetersFeatureStatistics | 2 |  | Anil |  | Anil | Done
GroupFeatures | 2 |  | Anil |  | Anil | Done
QueueConfiguration(really ro) | 3 |  | TBD |  | TBD |  |  | Does not exist, is read only
Stats
Groups | 2 |  | Anil |  | Anil | Done
Meters | 2 |  | Anil |  | Anil | Done
Tables | 2 |  | Anil |  | Anil | Done
Flows | 1 |  | Anil |  | Anil | Done
Ports | 1 |  | Anil |  | Anil | Done
Queues | 3 |  | Anil |  | Anil | Done
Errors | 1 |  |  |  | Prasana | Done
Adaptors
Topology | 1 | Depends on Topology MD-NSF, Inventory-Adaptor |  |  | eaw | Done |  | Pending merge - Bug fixing
FRM | 1 | Flow MD-NSF, Inventory-Adaptor |  |  | Moiz | 2013-12-20 | 2014-01-06
SwitchManager (Inventory) | 1 | FlowCapableInventoryManager, Switch Features OpState |  |  | Moiz | Done
Statistics Manager | 1 | Flow and Port MD-Stats, Flow Adaptor |  |  | Anil | Done
IPluginOut |  |  |  |  | Anil | Done
IPluginIn |  |  |  |  | eaw | Done
Host Tracker | 1 | MD-Hosttracker |  |  | TBD | ETA: 12/20 |  | Investigation to commence on 12/16 (Vaclav and Juraj)
Arp Handler | 1 | MD-HostTracker, MD-Arphandler |  |  | TBD | ETA: 12/20 |  | Investigation to commence on 12/16 (Vaclav and Juraj)
Troubleshooting Manager |  |  |  |  | TBD | ETA: 12/20 |  | Investigation to commence on 12/16 (Vaclav and Juraj)
PCE | 1
PacketIn | 1 | MD-PacketIn |  |  | Juraj | Done
PacketOut | 1 | MD-PacketOut |  |  | Vaclav,Juraj | Done |  | Code to be pushed to plugin, then merged
PacketOut | 1 |  | If needed, check with Michal |  | Vaclav | Done |  | Works - being moved to converter, will merge working bit by 9:30am PST
OF 1.0 | 1 | [6 empty] | Needs testing, expect lot of breakage
OF 1.0 infra | 1 |  | Michal Rehak | Michal Polkrab |  | Done |  | (will also have eth src and eth dst matches, packet in)
OF 1.0 actions | 1 |  | Ericsson | Ericsson |  | Done |  | All good but NW_DST/SRC and Gaurav is fixing 12/20
OF 1.0 matches | 1 |  | IBM/Michal Rehak | IBM/Michal Rehak |  | Done
OF 1.0 statistics | 1 |  | AnilG | AnilG |  | 2013-12-20 |  | There is a bug being investigated around reporting of multiple flow stats
OF 1.0 Asynchronous Messages | 1 |  | AnilG | AnilG |  | Done
OF 1.0 Packet Out | 1 |  | AnilG | AnilG |  | 2014-01-06
OF 1.0 testing | 1 |  | AnilG | AnilG |  | 2013-12-20 |  | Done but stats bug and packet out
OF 1.0 Barrier | 4 | Barrier | AnilG | AnilG |  | Done
Topology | 1 | PacketIn, PacketOut, Flow MD-NSF |  |  | Juraj, Vaclav
LLDPSpeaker (in plugin) | 1 | PacketOut |  |  | Ed | Done
LLDPListener (in NSF) | 1 | PacketIn, Flow MD-NSF |  |  |  | Done |  | Pending Merge
ArpHander |  | PacketIn, PacketOut, Flow MD-NSF |  |  | Ericsson |  |  | We only want to do these if we need them to do topology
HostTracker |  | MD-ArpHandler |  |  | Juraj, Vaclav |  |  | We only want to do these if we need them to do topology
Bug fixing |  |  | All | All | All | Ongoing
All needed messages accepted by switch | 1 |  | Ericsson/Michals | Ericsson/Michals |  |  |  | ETA Due tomorrow jointly from Prasanna and MichalP
Barrier | 4 |  | Ericsson/Michals | Ericsson/Michals |  | Done |  | Consider whether to send barrier between each flow https://git.opendaylight.org/gerrit/#/c/3825/
Drop-Test | 2 | OF 1.0 |  |  |  | Done
Test with Clustering | 1 |  |  |  | Probably Moiz |  |  | Ed to get ETA by 12/17
OF 1.0 to point of performance testing |  |  |  |  | Michal | Done |  | Will be done as part of OF 1.0 infra work
TLS Testing | [7 empty] | Needs to be done with a Private Certificate
RESTCONF Testing | 1 |  | Jan | Jan |  | 2014-01-06 |  | Progress ongoing on scripts